## Sheet1
Schedule & Plan Completion Dates |  | Allowed | NEW | Comments
|  | # Days | Examiners
Module Availibility |  |  | `11/4
Call Session- Cohorts with Facilitators*
Conference call-Discuss process , Use of Digital Chalk, facilitator reviews, Case Study review suggestions, Contact Info |  |  | call11/5 | Sat NOON-1:00PM
Module E-2 - Ethics and Examiner Guidelines |  | 2 | `11/8 | Print , sign and bring ethics form to training
Module E-3, KYCPE Processes |  | 2 | `11/10
Module E-4 -2015-16 Criteria for Performance Excellence |  | 3 | `11/13
Module E-5 - Key Terms |  | 2 | `11/15
Module E-6 - Documentation for Independent Review |  | 3 | `11/18
Call -Case Study evaluation suggestions-Open forum |  |  | Call 11/19
Module E-7 - Organizational Profile(OP) bring key factors to training | Complete #9-17, 39-40 | 4 | `11/22 | See QE KF examples #1-8,18-38,41-42
Thanksgiving break -4days no rqmts-Catchup up time if needed |  |  | `11/23-26 | Four Days -Thanksgiving break
Module E-8 - Evaluating and Scoring Processes -One Item | Complete 5.1 exercise&submit | 5 | `12/01 | See QE 5.2 completed example
Module E-9 - Evaluating and Scoring Results -One Item | Complete 7.3 exercise&submit | 4 | `12/05 | See QE 7. 2 completed example
Module E-10 - Comment Writing | Complete for 5.1& 7.3&submit | 4 | `12/09 | See QE 5.2 & 7.2 completed examples
Module E-11 - Pre-Consensus process |  | 1 | `12/10
Work time |  | 31
Elapsed time |  | 34
Done |  |  | `12/10 | Print out course completion certificate
Excel file documentation issues, Evidence and Comment Writing 'attempts', open forum (conference call if needed) |  | Sat AM | call 12/10
IWU Training start |  |  | `12/13
* Note: all calls acheduled for Sat AM