**Team Leader Checklist**

|  |  |
| --- | --- |
| **STEPS** | **ACTIONS** |
| **Getting Started** | * Send team welcome email and request Biography Forms and Calendar Forms from team members; ensure no conflicts of interest
* Contact applicant for introductions and to determine site visit dates
* Set and distribute team calendar
* Host a team call to cover team introductions, calendar, and independent review instructions
* Begin logistics planning for consensus and site visit (location, hotels, etc.)
 |
| **Stage 1 – Managing Independent Review** | * Consider reviewing key factors and item 1.1 for each team member during the first week to make sure everyone is on track
* Check in with new examiners and those who may be struggling throughout independent review
* Monitor work and follow up with any stragglers
 |
| **Stage 2 – Consensus Review *w/o* Site visit** | * Host a team call to review instructions and expectations for consensus
* Monitor work and follow up with any stragglers
* Distribute consensus meeting agenda and consensus script
* Manage consensus meeting, including identification of key themes.
* Set final due date for team members to finalize item comments.
* Read and edit the final scorebook before turning in to TNCPE
* Forward all final documents to KyCPE.
 |
| **Stage 2 – Consensus Review *with* Site visit** | * Host a team call to review instructions and expectations for consensus
* Monitor work and follow up with any stragglers
* Distribute consensus meeting agenda and consensus script
* Manage consensus meeting, including identification of key themes and site visit issues
* Notify KyCPE when consensus scorebook is final.
* If site visit is not conducted,
* Watch just-in-time site visit preparation video with team
 |
| **Stage 3 – Site Visit(Preparation)** | * Collect site visit **questions** and document requests from team members
* Provide applicant site visit agenda, questions, and document requests 1-2 weeks prior to site visit
* Collect and review completed site visit issue **worksheets** from team members
 |
| **(On Site)** | * Conduct opening meeting, daily caucus meeting(s), and closing meeting
* Manage site visit, including checking in with applicant daily and monitoring team member progress (make sure there are solid strengths and OFIs for each item)
* Maintain interview and document logs on site
 |
| **Stage 4 – Finalize Feedback Report** | * Manage wrap up meeting, including finalizing all item comments and key themes
* Complete Summary of Site Visited, Score Summary Worksheet with scoring band descriptors, and Award Recommendation Form with team
* Set final due date for team members to finalize item comments and hand in completed site visit issue worksheets
* Read and edit the final scorebook before turning in to TNCPE
* Forward all final documents to KyCPE, including team hours tracking sheet
 |